## FERIA Cleaning
ŠKODA WDC 2019 SCALA |  |  |  |  | Business Meeting (BM) - Pavillon 5 (P5) Level 1
Get Together (GT) - Pavillon 5 (P5) Level 1
1. DRAFT / CLEANING TIMING PLAN FERIA VALENCIA |  |  |  |  | Exhibition (EXH) - Pavillon 5 (P5) Level 1
Farwell Lunch - Pavillon 5 (P5) Level 4
Status: |  |  |  |  | Foro Centro - Level 4
Author: |  | CFR |  |  | Overall all areas incl. Offices (stand by team)
Responsibilities:
ŠKODA
adhoc4acp GmbH |  |  | Agency |  | coordination
FERIA VALENCIA |  |  | Venue |  | Cleaning Team
No. | Time Start | Time End | Duration | Action | Who | Cleaning Team | Projectmanagement adhoc | Notes | staff | total hours
Wednesday, 04.10.2017
Thursday, 05.10.2017
Friday, 06.10.2017
Thursday, 21.03.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
0
Friday, 22.03.2019 | [9 empty] | 0
0
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
0
Saturday, 23.03.2019 | [9 empty] | 0
0
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
0
0
Sunday, 24.03.2019 | [9 empty] | 0
0
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
0
0
Monday, 25.03.2019 | [9 empty] | 0
0
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
0
Tuesday, 26.03.2019 | [9 empty] | 0
0
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 10:00 | 18:00 | 8 | Cleaning of stage / floors / carpets / seats | Cleaning team | x |  |  |  | 0
Wednesday, 27.03.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
EXH | 10:00 | 18:00 | 8 | Deep cleaning of floors and area | Cleaning team | x | x
Thursday, 28.03.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Cleaning of stage / floors / carpets / seats | Cleaning team | x | x
| 13:00 | 15:00 | 2:00 | Cleaning of stage / floors / carpets / seats / | Cleaning team | x | x
| 18:00 | 20:00 | 2:00 | Deep cleaning of stage / floors / carpets / seats | Cleaning team | x | x
Friday, 29.03.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Cleaning of stage / floors / carpets / seats | Cleaning team | x | x
| 9:00 | 11:00 | 2 | Technical Rehearsals with all parties | ALL | x | x
| 11:00 | 11:45 | 0.75 | Break | ALL | x | x
BM | 11:00 | 11:45 | 0.75 | Cleaning stage area | Cleaning team | x | x |  |  | 0
| 11:45 | 18:00 | 6.25 | Technical Rehearsals with all parties | ALL | x | x
| 18:00 | 19:00 | 1 | Day-out Meeting | ALL | x | x
BM | 18:00 | 21:00 | 3 | Deep cleaning of stage / floors / carpets / seats | Cleaning team | x | x
Saturday, 30.03.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
Foro Centro | 7:00 | 12:00 | 5 | Cleaning of floors/area | Cleaning team | x |  |  |  | 0
Farewell Lunch | 7:00 | 12:00 | 5 | Cleaning of floors/area | Cleaning team | x
BM | 7:00 | 12:00 | 5 | Cleaning of stage / floors / carpets / seats | Cleaning team | x | x
| 9:00 | 11:00 | 2 | Technical Rehearsals with all parties | ALL | x | x
| 11:00 | 11:45 | 0.75 | Break | ALL | x | x
BM | 11:00 | 11:45 | 0.75 | Cleaning stage area | Cleaning team | x | x
| 11:30 | 12:00 | 0.5 | Preparation of Catering refreshments for Speakers | EJ/AS | x | x
| 11:45 | 12:00 | 0.25 | Stand-by all for rehearsal with Speakers | ALL | x | x
| 12:00 | 13:00 | 1 | Rehearsal Speaker | Speakers, ALL | x | x
| 13:00 | 14:00 | 1 | Rehearsal Speaker | ALL | x | x
| 14:30 | 15:30 | 1 | Rehearsal Speaker | Speakers, ALL | x | x
| 15:30 | 16:30 | 1 | Rehearsal Speaker | Speakers, ALL, | x | x
| 14:00 | 14:30 | 0.5 | Break | Speakers, ALL | x | x
BM | 14:00 | 14:30 | 0.5 | Cleaning stage area | Cleaning team | x | x
| 16:30 | 18:00 | 1.5 | BM Rundown with all parties | Speakers, ALL | x | x
| 18:00 | 19:00 | 1 | Day-out Meeting | ALL | x | x
BM | 18:00 | 21:00 | 3 | Deep cleaning of stage / floors / carpets / seats | Cleaning team | x | x
Sunday, 31.03.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 8:00 | 14:30 | 6.5 | Cleaning of stage / floors / carpets / seats | Cleaning team | x | x
| 9:00 | 11:00 | 2 | Technical Rehearsals with all parties | ALL | x | x
| 11:00 | 11:45 | 0.75 | Break | ALL | x | x
BM | 11:00 | 11:45 | 0.75 | Cleaning stage area | Cleaning team | x | x
| 11:00 | 12:00 | 1 | Cleaning of cars and stage | Cleaning team | x | x
| 11:30 | 12:00 | 0.5 | Preparation of Catering refreshments for Speakers | EJ/AS | x | x
| 11:45 | 12:00 | 0.25 | Stand-by all for rehearsal with Speakers | ALL | x | x
| 12:00 | 13:30 | 1.5 | BM Rundown with all parties | Speakers, ALL | x | x
| 13:30 | 15:00 | 1.5 | Break for Speakers | Speakers | x | x
| 13:30 | 14:30 | 1 | Lunch Break for BM team | ALL | x | x
BM | 13:30 | 14:30 | 1 | Cleaning of cars and stage area | Cleaning team | x | x
| 14:30 | 15:00 | 0.5 | Adjustments & further programming of AVL | AVL Operator, Camera Crew | x | x
| 15:00 | 15:00 | 0 | Stand-by all for rehearsal with Speakers | ALL | x | x
| 15:00 | 16:30 | 1.5 | BM Rundown with all parties | Speakers, ALL | x | x
| 16:30 | 17:00 | 1.5 | Break |  | x | x
| 17:00 | 19:00 | 2 | Technical Rehearsals with all parties | ALL | x | x
BM | 18:30 | 20:00 | 1.5 | Deep cleaning of stage / floors / carpets / seats | Cleaning team | x | x
GT | 18:30 | 22:00 | 3.5 | Get Together Area counters / bars / coffee stations
Monday, 01.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x |  |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Deep Cleaning of stage / floors / carpets / seats | Cleaning team | x
Foro Centro | 8:00 | 10:00 | 2 | Cleaning of floor/area | cleaning team | x
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations | Cleaning team | x
| 10:00 | 14:00 | 4 | Possible rehearsal time slot | ALL |  | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
BM | 15:00 | 17:00 | 2 | Collect garbage / cleaning of stage | Cleaning team | x
| 17:15 | 17:45 | 0.5 | All stand-by for show | ALL |  | x
| 17:45 | 18:15 | 0.5 | Guest Arrival |  |  | x
| 18:30 | 20:15 | 1.75 | BUSINESS MEETING SHOW |  |  | x
BM | 20:30 | 0:00 | 3.5 | Deep Cleaning of stage / floors / carpets / seats |  | x
GT | 20:30 | 0:00 | 3.5 | Get Together Area counters / bars / coffee stations/ floor |  | x
EXH | 20:30 | 0:00 | 3.5 | Deep cleaning of floors | Cleaning team | x
Tuesday, 02.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Deep Cleaning of stage / floors / carpets / seats | Cleaning team | x
Foro Centro | 8:00 | 10:00 | 2 | Cleaning of floor/area | cleaning team | x
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations/ floor | Cleaning team | x
| 10:00 | 14:00 | 4 | Possible rehearsal time slot | ALL |  | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
BM | 15:00 | 17:00 | 2 | Collect garbage | Cleaning team | x
| 17:15 | 17:45 | 0.5 | All stand-by for show | ALL |  | x
| 17:45 | 18:15 | 0.5 | Guest Arrival |  |  | x
| 18:30 | 20:15 | 1.75 | BUSINESS MEETING SHOW |  |  | x
BM | 20:30 | 0:00 | 3.5 | Deep Cleaning of stage / floors / carpets / seats |  | x
GT | 20:30 | 0:00 | 3.5 | Get Together Area counters / bars / coffee stations/ floor |  | x
EXH | 20:30 | 0:00 | 3.5 | Deep cleaning of floors / collect garbage | Cleaning team | x
Wednesday, 03.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Deep Cleaning of stage / floors / carpets / seats | Cleaning team | x
Foro Centro | 8:00 | 10:00 | 2 | Cleaning of floor/area | cleaning team | x
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations | Cleaning team | x
| 10:00 | 14:00 | 4 | Possible rehearsal time slot | ALL |  | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
BM | 15:00 | 17:00 | 2 | Collect garbage | Cleaning team | x
| 17:15 | 17:45 | 0.5 | All stand-by for show | ALL |  | x
| 17:45 | 18:15 | 0.5 | Guest Arrival |  |  | x
| 18:30 | 20:15 | 1.75 | BUSINESS MEETING SHOW |  |  | x
BM | 20:30 | 0:00 | 3.5 | Deep Cleaning of stage / floors / carpets / seats |  | x
GT | 20:30 | 0:00 | 3.5 | Get Together Area counters / bars / coffee stations/ floor |  | x
EXH | 20:30 | 0:00 | 3.5 | Deep cleaning of floors / collect garbage | Cleaning team | x
Thursday, 04.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Deep Cleaning of stage / floors / carpets / seats | Cleaning team | x
Foro Centro | 8:00 | 10:00 | 2 | Cleaning of floor/area | cleaning team | x
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations | Cleaning team | x
| 10:00 | 14:00 | 4 | Possible rehearsal time slot | ALL |  | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
BM | 15:00 | 17:00 | 2 | Collect garbage | Cleaning team | x
| 17:15 | 17:45 | 0.5 | All stand-by for show | ALL |  | x
| 17:45 | 18:15 | 0.5 | Guest Arrival |  |  | x
| 18:30 | 20:15 | 1.75 | BUSINESS MEETING SHOW |  |  | x
BM | 20:30 | 0:00 | 3.5 | Deep Cleaning of stage / floors / carpets / seats |  | x
GT | 20:30 | 0:00 | 3.5 | Get Together Area counters / bars / coffee stations/ floor |  | x
EXH | 20:30 | 0:00 | 3.5 | Deep cleaning of floors / collect garbage | Cleaning team | x
Friday, 05.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Deep Cleaning of stage / floors / carpets / seats | Cleaning team | x
Foro Centro | 8:00 | 10:00 | 2 | Cleaning of floor/area | cleaning team | x
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations | Cleaning team | x
| 10:00 | 14:00 | 4 | Possible rehearsal time slot | ALL |  | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
BM | 15:00 | 17:00 | 2 | Collect garbage | Cleaning team | x
| 17:15 | 17:45 | 0.5 | All stand-by for show | ALL |  | x
| 17:45 | 18:15 | 0.5 | Guest Arrival |  |  | x
| 18:30 | 20:15 | 1.75 | BUSINESS MEETING SHOW |  |  | x
BM | 20:30 | 0:00 | 3.5 | Deep Cleaning of stage / floors / carpets / seats |  | x
GT | 20:30 | 0:00 | 3.5 | Get Together Area counters / bars / coffee stations/ floor |  | x
EXH | 20:30 | 0:00 | 3.5 | Deep cleaning of floors / collect garbage | Cleaning team | x
Saturday, 06.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Deep Cleaning of stage / floors / carpets / seats | Cleaning team | x
Foro Centro | 8:00 | 10:00 | 2 | Cleaning of floor/area | cleaning team | x
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations | Cleaning team | x
| 10:00 | 14:00 | 4 | Possible rehearsal time slot | ALL |  | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
BM | 15:00 | 17:00 | 2 | Collect garbage | Cleaning team | x
| 17:15 | 17:45 | 0.5 | All stand-by for show | ALL |  | x
| 17:45 | 18:15 | 0.5 | Guest Arrival |  |  | x
| 18:30 | 20:15 | 1.75 | BUSINESS MEETING SHOW |  |  | x
BM | 20:30 | 0:00 | 3.5 | Deep Cleaning of stage / floors / carpets / seats |  | x
GT | 20:30 | 0:00 | 3.5 | Get Together Area counters / bars / coffee stations/ floor |  | x
EXH | 20:30 | 0:00 | 3.5 | Deep cleaning of floors / collect garbage | Cleaning team | x
Sunday, 07.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Deep Cleaning of stage / floors / carpets / seats | Cleaning team | x
Foro Centro | 8:00 | 10:00 | 2 | Cleaning of floor/area | cleaning team | x
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations | Cleaning team | x
| 10:00 | 14:00 | 4 | Possible rehearsal time slot | ALL |  | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
BM | 15:00 | 17:00 | 2 | Collect garbage | Cleaning team | x
| 17:15 | 17:45 | 0.5 | All stand-by for show | ALL |  | x
| 17:45 | 18:15 | 0.5 | Guest Arrival |  |  | x
| 18:30 | 20:15 | 1.75 | BUSINESS MEETING SHOW |  |  | x
BM | 20:30 | 0:00 | 3.5 | Deep Cleaning of stage / floors / carpets / seats |  | x
GT | 20:30 | 0:00 | 3.5 | Get Together Area counters / bars / coffee stations/ floor |  | x
EXH | 20:30 | 0:00 | 3.5 | Deep cleaning of floors / collect garbage | Cleaning team | x
Monday, 08.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Deep Cleaning of stage / floors / carpets / seats | Cleaning team | x
Foro Centro | 8:00 | 10:00 | 2 | Cleaning of floor/area | cleaning team | x
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations | Cleaning team | x
| 10:00 | 14:00 | 4 | Possible rehearsal time slot | ALL |  | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
BM | 15:00 | 17:00 | 2 | Collect garbage | Cleaning team | x
| 17:15 | 17:45 | 0.5 | All stand-by for show | ALL |  | x
| 17:45 | 18:15 | 0.5 | Guest Arrival |  |  | x
| 18:30 | 20:15 | 1.75 | BUSINESS MEETING SHOW |  |  | x
BM | 20:30 | 0:00 | 3.5 | Deep Cleaning of stage / floors / carpets / seats |  | x
GT | 20:30 | 0:00 | 3.5 | Get Together Area counters / bars / coffee stations/ floor |  | x
EXH | 20:30 | 0:00 | 3.5 | Deep cleaning of floors / collect garbage | Cleaning team | x
Tuesday, 09.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Deep Cleaning of stage / floors / carpets / seats | Cleaning team | x
Foro Centro | 8:00 | 10:00 | 2 | Cleaning of floor/area | cleaning team | x
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations | Cleaning team | x
| 10:00 | 14:00 | 4 | Possible rehearsal time slot | ALL |  | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
BM | 15:00 | 17:00 | 2 | Collect garbage | Cleaning team | x
| 17:15 | 17:45 | 0.5 | All stand-by for show | ALL |  | x
| 17:45 | 18:15 | 0.5 | Guest Arrival |  |  | x
| 18:30 | 20:15 | 1.75 | BUSINESS MEETING SHOW |  |  | x
BM | 20:30 | 0:00 | 3.5 | Deep Cleaning of stage / floors / carpets / seats |  | x
GT | 20:30 | 0:00 | 3.5 | Get Together Area counters / bars / coffee stations/ floor |  | x
EXH | 20:30 | 0:00 | 3.5 | Deep cleaning of floors / collect garbage | Cleaning team | x
Wednesday, 10.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Deep Cleaning of stage / floors / carpets / seats | Cleaning team | x
Foro Centro | 8:00 | 10:00 | 2 | Cleaning of floor/area | cleaning team | x
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations | Cleaning team | x
| 10:00 | 14:00 | 4 | Possible rehearsal time slot | ALL |  | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
BM | 15:00 | 17:00 | 2 | Collect garbage | Cleaning team | x
| 17:15 | 17:45 | 0.5 | All stand-by for show | ALL |  | x
| 17:45 | 18:15 | 0.5 | Guest Arrival |  |  | x
| 18:30 | 20:15 | 1.75 | BUSINESS MEETING SHOW |  |  | x
BM | 20:30 | 0:00 | 3.5 | Deep Cleaning of stage / floors / carpets / seats |  | x
GT | 20:30 | 0:00 | 3.5 | Get Together Area counters / bars / coffee stations/ floor |  | x
EXH | 20:30 | 0:00 | 3.5 | Deep cleaning of floors / collect garbage | Cleaning team | x
Thursday, 11.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
BM | 6:00 | 10:00 | 4 | Deep Cleaning of stage / floors / carpets / seats | Cleaning team | x
Foro Centro | 8:00 | 10:00 | 2 | Cleaning of floor/area | cleaning team | x
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations | Cleaning team | x
| 10:00 | 14:00 | 4 | Possible rehearsal time slot | ALL |  | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
BM | 15:00 | 17:00 | 2 | Collect garbage | Cleaning team | x
| 17:15 | 17:45 | 0.5 | All stand-by for show | ALL |  | x
| 17:45 | 18:15 | 0.5 | Guest Arrival |  |  | x
| 18:30 | 20:15 | 1.75 | BUSINESS MEETING SHOW |  |  | x
BM | 20:30 | 0:00 | 3.5 | Deep Cleaning of stage / floors / carpets / seats |  | x
GT | 20:30 | 0:00 | 3.5 | Get Together Area counters / bars / coffee stations/ floor |  | x
EXH | 20:30 | 0:00 | 3.5 | Deep cleaning of floors / collect garbage | Cleaning team | x
Friday, 12.04.2019
Overall (incl Offices) | 10:00 | 18:00 | 8 | Cleaning Team (2 pax) for all day issues | Cleaning Team Location | x | x |  | 2 | 16
GT + EXH | 10:00 | 14:00 | 4 | Get Together Area counters / bars / coffee stations | Cleaning team | x
Farewell Lunch | 14:00 | 17:00 | 3 | cleaning whole area | Cleaning team | x
DURING DISMANTLING | 8.00 | 20:00
[8 empty] | TOTAL | 46 | 368